{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Erhaltungsprojekte_laufendes_J","Tabelle1","Tabelle3","Änderungsnachweis"],"not_rendered":{"charts":0,"images":1,"macros":1,"external_links":0,"defined_names":5,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Erhaltungsprojekte_laufendes_J","index":0,"n_rows":23,"n_cols":15,"rows_kept":23,"cut":false,"hidden":false,"merged":[[0,3,0,4],[3,0,3,4]]}
["Staatliches Bauamt Landshut",null,null,"2023-03-30"]
[]
[]
[{"$f":"\"aktuelles Bauprogramm Bestandserhaltung \" & YEAR(D1) &CHAR(10) & \">= 0,3 Mio. €\"","v":"aktuelles Bauprogramm Bestandserhaltung 2023\n>= 0,3 Mio. €"}]
[]
["lfd. Nr. ","Straße","Projektbezeichnung","Baulänge/\nBauwerksfläche","Gesamtkosten",null,null,"Landkreis","Projektstatus","MS BAU","MS BE","Kennung","Fachprogramm","Baulänge","BW-Fläche"]
[1,"B 15","Instandsetzung Hachelstuhler Berg",0.05,0.74199999999999999,null,{"$f":"\"P\"","v":"P"},"LA","BAU","2018-06-11","2023-06-01","B21S.BBBC0085.00","Erhaltung Strecke BStr",0.05]
[2,"B 15n","Instandsetzung nördl AS Schierling Nord",3.2,3.65,null,"P","KEH","BV","2023-04-17","2023-06-19","B21S.ABBC0037.00","Erhaltung Strecke BStr",3.2]
[3,"B 15n","Mannsdorf - AS Neufahrn Fugensanierung Betonfahrbahn",10.09,1,null,"P","LA","BV","2023-05-05","2023-10-31","B21S.BBBC0110.00","Erhaltung Strecke BStr",10.09]
[4,"B 15n","Instandsetzung Bauwerk K25/1",258,0.3,null,"P","SR","BV","2023-07-07","2023-10-06","B21S.BBBD0116.00","Erhaltung Bauwerke BStr",4.2999999999999997E-2,258]
[5,"B 16","Erneuerung Brücke über KEH19 bei Saal a.d.Donau",91,3.6,null,"P","KEH","BAU","2022-04-04","2023-04-07","B21S.BBBD0113.00","Erhaltung Bauwerke BStr",7.0000000000000001E-3,91]
[6,"B 20","Instandsetzung Brücke über St 2113 bei Landau",496,1.2,null,"P","DGF","BV","2023-04-03","2023-10-27","B21S.BBBD0108.00","Erhaltung Bauwerke BStr",2.9000000000000001E-2,496]
[7,"B 299","Instandsetzung Brücke über die Donau und Ilm bei Neustadt",6629,4.95,null,"P","KEH","BV","2023-04-03","2024-12-13","B21S.ABBD0039.00","Erhaltung Bauwerke BStr",0.44600000000000001,6629]
[8,"B 299","Instandsetzung Kreisverkehrsplatz Arth bis Anschlussstelle Altdorf",3.1749999999999998,1.65,null,"P","LA","BV","2023-07-07","2023-09-10","B21S.BBBC0102.00","Erhaltung Strecke BStr",3.1749999999999998]
[9,"B 301","Instandsetzung OD Mainburg",1.7,2.6,null,"P","KEH","BV","2023-08-04","2025-12-01","B21S.BBBC0091.00","Erhaltung Strecke BStr",1.7]
[10,"St 2054","Instandsetzung östl. Altfraunhofen",5.95,1.5,null,"P","LA","BV","2023-08-14","2023-11-08","B21S.BLSC0085.00","Erhaltung Strecke SStr",5.95]
[11,"St 2074","Instandsetzung bei Unterahrain",4.5759999999999996,1.8,null,"P","LA","BV","2023-07-01","2023-09-01","B21S.BLSC0099.00","Erhaltung Strecke SStr",4.5759999999999996]
[12,"St 2083","Instandsetzung Frontenhausener Straße in Vilsbiburg",1.4,5.0600000000000005,null,"P","LA","UB","2022-07-04","2023-10-31","B21S.BLSC0205.00","Erhaltung Strecke SStr",1]
[13,"St 2087","Instandsetzung Brücke über Vilsflutgraben bei Altfraunhofen",179,0.55000000000000004,null,"P","LA","BV","2023-04-03","2023-10-27","B21S.BLSD0192.00","Erhaltung Bauwerke SStr",1.7000000000000001E-2,179]
[14,"St 2111","Instandsetzung Frontenhausener Str. in Dingolfing",1.5780000000000001,0.8,null,"P","DGF","BV","2023-08-09","2023-10-24","B21S.BLSC0197.00","Erhaltung Strecke SStr",1.5780000000000001]
[15,"St 2142","Erneuerung Brücke über Bach bei Thonhausen",40,0.7,null,"P","LA","BV","2023-08-14","2023-10-27","B21S.BLSD0200.00","Erhaltung Bauwerke SStr",4.0000000000000001E-3,40]
[16,"St 2333","Instandsetzung westlich Kirchdorf",4.3,1.1000000000000001,null,"P","KEH","BV","2023-08-01","2023-11-25","B21S.BLSB0149.00","Erhaltung Strecke SStr",4.3]
[17,"St 2643","Erneuerung der Brücke über den Marktbach in Pfeffenhausen",25,0.3,null,"P","LA","BV","2023-07-21","2023-10-06","B21S.BLSD0171.00","Erhaltung Bauwerke SStr",3.0000000000000001E-3,25]

{"sheet":"Tabelle1","index":1,"n_rows":4,"n_cols":27,"rows_kept":4,"cut":false,"hidden":true,"merged":[]}
[1,2,3,"2018-03-20",5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26]
[null,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26]
[]
["lfd. Nr. ","Straße","Projektbezeichnung","Baulänge/\nBW-Fläche","Gesamtkosten\n[Mio. €]",null,null,"Landkreis","Status","MS BAU","MS BE","Kennung","Fachprogramm","Baulänge","BW-Fläche"]

{"sheet":"Tabelle3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Änderungsnachweis","index":3,"n_rows":19,"n_cols":3,"rows_kept":19,"cut":false,"hidden":true,"merged":[[9,1,9,2],[2,0,2,2],[4,1,4,2],[6,1,6,2],[7,1,7,2],[8,1,8,2],[23,1,23,2],[10,1,10,2],[11,1,11,2],[12,0,12,2],[18,0,18,2],[20,1,20,2],[22,1,22,2]]}
["Version:"]
[]
["Inhalte"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["Änderungsnachweise"]
["Datum","Beschreibung","Bearbeiter"]
["2018-05-23","Spaltenhöhe in Spalte C angepasst","SF"]
[]
[]
[]
["Plausiprüfung"]