{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Erhaltungsprojekte_laufendes_J","Tabelle1","Tabelle3","Änderungsnachweis"],"not_rendered":{"charts":0,"images":1,"macros":1,"external_links":0,"defined_names":5,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Erhaltungsprojekte_laufendes_J","index":0,"n_rows":22,"n_cols":15,"rows_kept":22,"cut":false,"hidden":false,"merged":[[0,3,0,4],[3,0,3,4]]}
["Staatliches Bauamt Landshut",null,null,"2022-03-21"]
[]
[]
[{"$f":"\"aktuelles Bauprogramm Bestandserhaltung \" & YEAR(D1) &CHAR(10) & \">= 0,3 Mio. €\"","v":"aktuelles Bauprogramm Bestandserhaltung 2022\n>= 0,3 Mio. €"}]
[]
["lfd. Nr. ","Straße","Projektbezeichnung","Baulänge/\nBauwerksfläche","Gesamtkosten",null,null,"Landkreis","Projektstatus","MS BAU","MS BE","Kennung","Fachprogramm","Baulänge","BW-Fläche"]
[1,"B 15","Umbau Kupfereck in Landshut",0.25,4.4000000000000004,null,{"$f":"\"P\"","v":"P"},"LA","BV","2022-03-29","2023-02-11","B21S.BBBB0092.00","Erhaltung Strecke BStr",0.25]
[2,"B 15n","Instandsetzung bei AS Schierling Süd",3.7930000000000001,2.4,null,{"$f":"\"P\"","v":"P"},"R","BV","2022-09-10","2022-11-05","B21S.ABBC0039.00","Erhaltung Strecke BStr",3.7930000000000001,0]
[3,"B 16","Erneuerung Brücke über K-KEH19 bei Saal a.d.Donau",91,1.5,null,{"$f":"\"P\"","v":"P"},"KEH","BV","2022-04-04","2023-04-07","B21S.BBBD0113.00","Erhaltung Bauwerke BStr",7.0000000000000001E-3,91]
[4,"B 16","Instandsetzung Brücke GVS über B16 bei Reißing",287,0.5,null,{"$f":"\"P\"","v":"P"},"KEH","BV","2022-04-04","2023-04-14","B21S.BBBD0115.00","Erhaltung Bauwerke BStr",4.1000000000000002E-2,287]
[5,"B 299","Instandsetzung bei Geisenhausen",3.9569999999999999,1.7,null,{"$f":"\"P\"","v":"P"},"LA","BV","2022-05-18","2022-11-05","B21S.BBBC0093.00","Erhaltung Strecke BStr",3.9569999999999999]
[6,"B 299","Instandsetzung Brücken bei Geisenhausen",1081,3.5,null,{"$f":"\"P\"","v":"P"},"LA","BV","2022-04-04","2023-04-28","B21S.BBBD0095.00","Erhaltung Bauwerke BStr",7.8E-2,1081]
[7,"St 2045","Instandsetzung Bruckbergerau",0.44700000000000001,0.35500000000000004,null,{"$f":"\"P\"","v":"P"},"LA","UB","2021-09-01","2022-04-18","B21S.BLSC0217.00","Erhaltung Strecke SStr",0.44700000000000001]
[8,"St 2049","Erneuerung Brücken über den Further Bach",383,3.25,null,{"$f":"\"P\"","v":"P"},"LA","BV","2022-06-01","2022-10-28","B21S.BLSD0170.00","Erhaltung Bauwerke SStr",2.4999999999999998E-2,383]
[9,"St 2083","Instandsetzung Frontenhausener Straße in Vilsbiburg",1,4.41,null,{"$f":"\"P\"","v":"P"},"LA","BV","2022-05-02","2023-10-31","B21S.BLSC0205.00","Erhaltung Strecke SStr",1]
[10,"St 2083","Instandsetzung OD Kröhstorf",0.98399999999999999,0.45,null,{"$f":"\"P\"","v":"P"},"DGF","BV","2022-04-19","2022-05-07","B21S.BLSC0211.00","Erhaltung Strecke SStr",0.98399999999999999]
[11,"St 2112","Instandsetzung östl Simbach",2.9940000000000002,0.9,null,{"$f":"\"P\"","v":"P"},"DGF","BAU","2022-03-05","2022-06-04","B21S.BLSC0195.00","Erhaltung Strecke SStr",2.9940000000000002]
[12,"St 2113","Erneuerung Brücke über Graben bei Rannersdorf",27,0.3,null,{"$f":"\"P\"","v":"P"},"DGF","OP","2022-07-04","2022-10-28","B21S.BLSD0194.00","Erhaltung Bauwerke SStr",2E-3,27]
[13,"St 2114","Instandsetzung OD Harburg",1.429,0.45,null,{"$f":"\"P\"","v":"P"},"DGF","BV","2022-07-21","2022-10-24","B21S.BLSC0187.00","Erhaltung Strecke SStr",1.429]
[14,"St 2141","Instandsetzung Postau - Hinzlbach",5.4329999999999998,2.1,null,{"$f":"\"P\"","v":"P"},"LA","UB","2021-08-30","2022-07-02","B21S.BLSC0060.00","Erhaltung Strecke SStr",5.4329999999999998,0]
[15,"St 2142","Instandsetzung Brücke über Kleine Laaber bei Hofendorf",431,0.85,null,{"$f":"\"P\"","v":"P"},"LA","BV","2022-04-18","2022-10-14","B21S.BLSD0176.00","Erhaltung Bauwerke SStr",4.1000000000000002E-2,431]
[16,"St 2143","Instandsetzung nördl Hohenthann",2.2570000000000001,0.8,null,{"$f":"\"P\"","v":"P"},"LA","BAU","2021-12-30","2022-11-05","B21S.BLSC0199.00","Erhaltung Strecke SStr",2.2570000000000001]

{"sheet":"Tabelle1","index":1,"n_rows":4,"n_cols":27,"rows_kept":4,"cut":false,"hidden":true,"merged":[]}
[1,2,3,"2018-03-20",5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26]
[null,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26]
[]
["lfd. Nr. ","Straße","Projektbezeichnung","Baulänge/\nBW-Fläche","Gesamtkosten\n[Mio. €]",null,null,"Landkreis","Status","MS BAU","MS BE","Kennung","Fachprogramm","Baulänge","BW-Fläche"]

{"sheet":"Tabelle3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Änderungsnachweis","index":3,"n_rows":19,"n_cols":3,"rows_kept":19,"cut":false,"hidden":true,"merged":[[9,1,9,2],[2,0,2,2],[4,1,4,2],[6,1,6,2],[7,1,7,2],[8,1,8,2],[23,1,23,2],[10,1,10,2],[11,1,11,2],[12,0,12,2],[18,0,18,2],[20,1,20,2],[22,1,22,2]]}
["Version:"]
[]
["Inhalte"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["Änderungsnachweise"]
["Datum","Beschreibung","Bearbeiter"]
["2018-05-23","Spaltenhöhe in Spalte C angepasst","SF"]
[]
[]
[]
["Plausiprüfung"]